## Project Plan and Gantt
Project Name | QuanLyGiangDay_TH
Project Manager | Phan Trung Hiếu
Project Deliverable
Scope Statement:
Start Date | 2016-08-19
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Phan Trung Hiếu | 2016-09-03 | 2016-09-04 | 1 | Complete
Agree on objectives | Phan Trung Hiếu | 2016-09-03 | 2016-09-04 | 1 | Complete
Detailed Reqs. | Trần Minh Phương | 2016-09-03 | 2016-09-04 | 1 | Complete
DB Development | Trần Minh Phương | 2016-09-05 | 2016-09-12 | 7 | Complete
Connect DB | Phan Trung Hiếu | 2016-09-05 | 2016-09-12 | 7 | Overdue
Form 1 | Phan Trung Hiếu | 2016-09-13 | 2016-09-21 | 8 | Overdue
Form 2 | Trần Minh Phương | 2016-09-13 | 2016-09-21 | 8 | Overdue
Function 1 | Phan Trung Hiếu | 2016-09-28 | 2016-10-05 | 7 | inprocess
Function 2 | Trần Minh Phương | 2016-09-28 | 2016-10-05 | 7 | inprocess
UI Client | Phan Trung Hiếu | 2016-09-28 | 2016-10-05 | 7 | inprocess
Testing | Trần Minh Phương | 2016-09-28 | 2016-10-05 | 7 | inprocess
Dev. Complete | Team | 2016-10-06 | 2016-10-08 | 2 | Not started
Hardware Config. | Phan Trung Hiếu | 2016-10-06 | 2016-10-08 | 2 | Not started
System Testing | Team | 2016-10-08 | 2016-10-09 | 1 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Phan Trung Hiếu | Team leader | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document | xburnpc@gmail.com
Trần Minh Phương | Developer | 1. Design GUI/database. 2. Code. 3. Test | phuongcntt10d@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team